## Sprint 1
Story ID | Task ID | Task Description | Estimate | Taken | Team Member | Date Completed |  | Items Left | 120 | Expected Left
3 | T001 | Create home, ToS and about us web pages | 1 | 1 | Charles Alleman | 2017-09-12 | Day 0 | 120 | 2017-08-30 | 120
3 | T002 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-25 | Day 1 | 120 | 2017-08-31 | 114
3 | T003 | Populate the pages with text appropriate to their name | 2 | 2 | Fahd | 2017-09-25 | Day 2 | 120 | 2017-09-01 | 108
3 | T004 | Verify story is complete (acceptance test) | 1 | 1 | Charles Alleman | 2017-09-25 | Day 3 | 120 | 2017-09-04 | 102
2 | T005 | Dev training on django database management | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 4 | 120 | 2017-09-05 | 96
2 | T006 | Create registration page with input form and submit button | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 5 | 120 | 2017-09-06 | 90
2 | T007 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-10 | Day 6 | 120 | 2017-09-07 | 84
2 | T008 | Create database | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 7 | 120 | 2017-09-08 | 78
2 | T009 | Create account table in database | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 8 | 120 | 2017-09-11 | 72
2 | T010 | Write code to input user data into database | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 9 | 86 | 2017-09-12 | 66
2 | T011 | Write code to check user data does not match another user in database | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 10 | 85 | 2017-09-13 | 60
2 | T012 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-09-10 | Day 11 | 81 | 2017-09-14 | 54
1 | T013 | Dev training on django session handling | 2 | 3 | Joshua Lowe | 2017-09-11 | Day 12 | 81 | 2017-09-15 | 48
1 | T014 | Add link to login page to public home page | 1 | 1 | Joshua Lowe | 2017-09-11 | Day 13 | 81 | 2017-09-18 | 42
1 | T015 | Create login page with input form | 1 | 1 | Charles Alleman | 2017-09-11 | Day 14 | 81 | 2017-09-19 | 36
1 | T016 | Create main page for logged in users with logout button | 2 | 1 | Charles Alleman | 2017-09-11 | Day 15 | 81 | 2017-09-20 | 30
1 | T017 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-11 | Day 16 | 68 | 2017-09-21 | 24
1 | T018 | Write code to check user credentials with database | 1 | 2 | Joshua Lowe | 2017-09-11 | Day 17 | 68 | 2017-09-22 | 18
1 | T019 | Write code to give user a login session | 3 | 0 | Joshua Lowe | 2017-09-11 | Day 18 | 52 | 2017-10-02 | 12
1 | T020 | Write code to navigate user to main page | 1 | 1 | Joshua Lowe | 2017-09-11 | Day 19 | 46 | 2017-10-03 | 6
1 | T021 | Write code to end the login session | 2 | 1 | Joshua Lowe | 2017-09-11 | Day 20 | 25 | 2017-10-04 | 0
1 | T022 | Write code to navigate user to public homepage after logout | 1 | 1 | Joshua Lowe | 2017-09-11
1 | T023 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-09-11
10 | T024 | Create admin creation page with input form | 1 | 0 | Joshua Lowe | 2017-09-10
10 | T025 | Create admin main page with link to admin creation page | 1 | 0 | Joshua Lowe | 2017-09-10
10 | T026 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-10
10 | T027 | Modify accounts table to allow different user types | 1 | 1 | Joshua Lowe | 2017-09-11
10 | T028 | Hard-code the initial admin account (owner) into the database | 1 | 1 | Joshua Lowe | 2017-09-10
10 | T029 | Create code to add new admin account to database | 2 | 0 | Joshua Lowe | 2017-09-10
10 | T030 | Create code to check admin data values do not match another user in database | 1 | 0 | Joshua Lowe | 2017-09-10
10 | T031 | Create code to display error message in creation failure | 2 | 0 | Joshua Lowe | 2017-09-10
10 | T032 | Verify the story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-09-10
7 | T033 | Dev training on django forms | 2 | 1 | Mikhail Burkot | 2017-09-26
7 | T034 | Create a modify account information page | 1 | 0.1 | Mikhail Burkot | 2017-09-13
7 | T035 | Create link to modify account information page from main page | 1 | 0.2 | Mikhail Burkot | 2017-09-13
7 | T036 | Create editable forms to hold account information | 2 | 0.5 | Mikhail Burkot | 2017-09-22
7 | T037 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-22
7 | T038 | Write code to populate forms containing account information from database | 2 | 1 | Mikhail Burkot | 2017-09-22
7 | T039 | Write code to save modifications to account information | 2 | 1.5 | Mikhail Burkot | 2017-09-22
7 | T040 | Write code to delete account | 1 | 1 | Mikhail Burkot | 2017-10-04
7 | T041 | Write code for password verification before committing changes | 1 | 1 | Mikhail Burkot | 2017-10-04
7 | T042 | Verify story is complete (acceptance test) | 1 | 1 | Mikhail Burkot | 2017-10-04
27 | T043 | Dev training on django timers | 1 | 1 | Charles Alleman | 2017-10-04
27 | T044 | Create link to enable admin user viewer on main page | 1 | 1 | Charles Alleman | 2017-10-04
27 | T045 | Create non-admin account for each user type in database | 1 | 1 | Charles Alleman | 2017-10-04
27 | T046 | Create list of possible times admin can stay in user viewer | 1 | 1 | Charles Alleman | 2017-10-04
27 | T047 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-04
27 | T048 | Write code to track time passed on server after a specified time | 1 | 0 | Charles Alleman | 2017-10-04
27 | T049 | Write code to log admin account into dummy account | 2 | 2 | Charles Alleman | 2017-10-04
27 | T050 | Write code to log admin back into admin account | 2 | 0 | Charles Alleman | 2017-10-04
27 | T051 | Write code to log admin back into admin account after certain time has passed | 2 | 1 | Charles Alleman | 2017-10-04
27 | T052 | Verify story is complete (acceptance test) | 2 | 1 | Charles Alleman | 2017-10-04
28 | T053 | Create admin delete account holder page with forms | 1 | 0 | Joshua Lowe | 2017-09-10
28 | T054 | Create link to admin delete account holder page on admin main page | 1 | 0 | Joshua Lowe | 2017-09-10
28 | T055 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-10
28 | T056 | Write code to delete specified user from the database | 1 | 1 | Joshua Lowe | 2017-09-10
28 | T057 | Verify story is complete (acceptance test) | 1 | 0.5 | Joshua Lowe | 2017-09-10
5 | T058 | Dev training on auto generating django pages based on url | 2 | 3 | Joshua Lowe | 2017-09-10
5 | T059 | Create locations table in database | 1 | 0.5 | Joshua Lowe | 2017-09-13
5 | T060 | Create empty view locations page | 1 | 1 | Joshua Lowe | 2017-09-20
5 | T061 | Create link to view locations page | 2 | 1 | Joshua Lowe | 2017-09-20
5 | T062 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-20
5 | T063 | Write code to generate content on view location page based on url | 5 | 1 | Joshua Lowe | 2017-09-13
5 | T064 | Write code to generate error message if url does not match to a database entry | 2 | 1 | Joshua Lowe | 2017-10-02
5 | T065 | Verify story is complete (acceptance test) | 2 | 2 | Joshua Lowe | 2017-10-02
6 | T066 | Create a search bar form on the main page | 1 | 2 | Joshua Lowe | 2017-10-03
6 | T067 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-03
6 | T068 | Write code to determine locations in database matching search bar input | 3 | 6 | Joshua Lowe | 2017-10-04
6 | T069 | Write code to update main page content with matching locations | 2 | 1 | Joshua Lowe | 2017-10-04
6 | T070 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-10-02
9 | T071 | Create modify location page with location search bar | 1 | 3 | Joshua Lowe | 2017-10-02
9 | T072 | Add link to modify location page on admin main page | 1 | 0.1 | Joshua Lowe | 2017-09-20
9 | T073 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-20
9 | T074 | Write code to determine locations in database matching search bar input | 1 | 1 | Joshua Lowe | 2017-09-20
9 | T075 | Write code to allow admin to select location to edit | 2 | 0 | Joshua Lowe | 2017-09-20
9 | T076 | Write code to allow admin to edit locations data | 2 | 0 | Joshua Lowe | 2017-09-20
9 | T077 | Write code to allow admin to save changes to database | 1 | 0 | Joshua Lowe | 2017-09-20
9 | T078 | Write code to allow admin to delete location from database | 1 | 0 | Joshua Lowe | 2017-09-20
9 | T079 | Write code to allow admin to deselect location | 2 | 0 | Joshua Lowe | 2017-09-20
9 | T080 | Verify story is complete (acceptance test) | 1 | 2 | Joshua Lowe | 2017-09-20
29 | T081 | Create suggested locations table in database | 1 | 0.2 | Joshua Lowe | 2017-10-03
29 | T082 | Create suggested location page | 1
29 | T083 | Add link to suggested location page on admin main page | 1
29 | T084 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-04
29 | T085 | Write code to display user suggested locations to admin | 2 | 0 | Joshua Lowe | 2017-10-03
29 | T086 | Write code to allow admin to approve location adding it to location table and remove entry from suggested locations table in database | 1
29 | T087 | Write code to allow admin to deny location removing entry from suggested locations table | 1 | 0 | Joshua Lowe | 2017-10-03
29 | T088 | Write code to allow admin to edit location data in suggested location | 2 | 0 | Joshua Lowe | 2017-10-03
29 | T089 | Verify story is complete (acceptance test) | 2
4 | T090 | Create map table in database | 1 | 0.5 | Joshua Lowe | 2017-10-04
4 | T091 | Create upload city map page with input form | 1
4 | T092 | Create link to upload city map page on admin main page | 1
4 | T093 | Write test cases | 1 | 1 | Mikhail Burkot
4 | T094 | Write code to upload city map to website | 2
4 | T095 | Write code to add city map and input field data to database | 2
4 | T096 | Verify story is complete (acceptance test) | 1
8 | T097 | Create view city map page with picture frame | 1
8 | T098 | Create link to view city map page on main page | 1
8 | T099 | Write test cases | 1 |  | Mikhail Burkot
8 | T100 | Write code to display city map for users location | 3
8 | T101 | Verify story is complete (acceptance test) | 1
26 | T102 | Create location images table in database | 1 |  | Joshua Lowe | 2017-09-20
26 | T103 | Create upload picture of location page with input form | 1
26 | T104 | Write test cases | 1 |  | Mikhail Burkot
26 | T105 | Write code to upload picture to website | 1 |  | Mikhail Burkot
26 | T106 | Write code to preview picture | 2
26 | T107 | Write code to add picture and input field data to database | 2
26 | T108 | Write code to deny upload of data to website | 1
26 | T109 | Write code to accept upload of data to website | 1
26 | T110 | Write code to change uploaded picture | 1
26 | T111 | Update view locations page to display pictures from database | 3
26 | T112 | Verify story is complete (acceptance test) | 1
17 | T113 | Dev training on sending emails with Python | 1 | 2 | Mikhail Burkot | 2017-10-04
17 | T114 | Create friend referral page with editable forms | 1 | 1 | Mikhail Burkot | 2017-09-29
17 | T115 | Create link to referral page on main page | 1 | 1 | Mikhail Burkot | 2017-09-29
17 | T116 | Create empty email account | 1 | 1 | Mikhail Burkot | 2017-09-29
17 | T117 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-09-29
17 | T118 | Write code to personalise email contents based on input form | 2 | 4 | Mikhail Burkot | 2017-10-04
17 | T119 | Write code to send email to recipient based on input form | 2 | 3 | Mikhail Burkot | 2017-10-04
17 | T120 | Verify story is complete (acceptance test) | 1 | 1 | Mikhail Burkot | 2017-10-04
|  |  | 163 | 95.1
Artefact ID | Artefact | Artefact Description | Team Member | Done?
1 | Architecture Pattern | Justification for selecting a specific architecture pattern for Smart City project | Ashley | Done
2 | Logical/Physical Diagram | Logical and Physical diagrams of the chosen architecture pattern for Smart City project | Ashley | Done
3 | Compenent Diagram | Compenent Diagram for Smart City project | Misha | Done
4 | Data Flow Diagram | Data Flow Diagram for Smart City project | Charles/Ashley | Done
5 | User Interface Design |  | Fahd/Charles | Done
6 | Design Class Diagram | Includes the Class Diagram (Josh), Object Diagram (Ashley), Sequence Diagram (Ashley), and Statechart Diagram (Misha). | Josh/Ashley/Misha | Done
7 | Data Model |  | Misha | Done
8 | Database Design |  | Misha | Done | [6 empty] | Sup
9 | SQL Scripts |  | Charles/Ashley | Done
10 | Test Data to Populate |  | Ashley | Done

## Sprint 2
Story ID | Task ID | Task Description | Estimate | Taken | Team Member | Date Completed |  | Items Left | 88 | Expected Left
4 | T001 | Create map table in database | 1 | 1 | Joshua Lowe | 2017-10-17 | Day 0 | 88 | 2017-10-09 | 88
4 | T002 | Create upload city map page with input form | 1 | 0 | Joshua Lowe | 2017-10-17 | Day 1 | 88 | 2017-10-10 | 83.6
4 | T003 | Create link to upload city map page on admin main page | 1 | 0 | Joshua Lowe | 2017-10-17 | Day 2 | 83 | 2017-10-11 | 79.2
4 | T004 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31 | Day 3 | 83 | 2017-10-12 | 74.8
4 | T005 | Write code to upload city map to website | 2 | 0 | Joshua Lowe | 2017-10-17 | Day 4 | 83 | 2017-10-13 | 70.4
4 | T006 | Write code to add city map and input field data to database | 2 | 0 | Joshua Lowe | 2017-10-17 | Day 5 | 70 | 2017-10-16 | 66
4 | T007 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-10-17 | Day 6 | 70 | 2017-10-16 | 61.6
8 | T008 | Create view city map page with picture frame | 1 | 1 | Joshua Lowe | 2017-10-17 | Day 7 | 70 | 2017-10-17 | 57.2
8 | T009 | Create link to view city map page on main page | 1 | 0 | Joshua Lowe | 2017-10-17 | Day 8 | 60 | 2017-10-18 | 52.8
8 | T010 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31 | Day 9 | 60 | 2017-10-19 | 48.4
8 | T011 | Write code to display city map for users location | 3 | 4 | Joshua Lowe | 2017-10-17 | Day 10 | 60 | 2017-10-20 | 44
8 | T012 | Verify story is complete (acceptance test) | 1 | 2 | Joshua Lowe | 2017-10-17 | Day 11 | 60 | 2017-10-23 | 39.6
26 | T013 | Create location images table in database | 1 | 1 | Mikhail Burkot | 2017-10-11 | Day 12 | 60 | 2017-10-24 | 35.2
26 | T014 | Create upload picture of location page with input form | 1 | 1 | Mikhail Burkot | 2017-10-11 | Day 13 | 60 | 2017-10-25 | 30.8
26 | T015 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31 | Day 14 | 60 | 2017-10-26 | 26.4
26 | T016 | Write code to upload picture to website | 1 |  | Mikhail Burkot | 2017-10-11 | Day 15 | 60 | 2017-10-27 | 22
26 | T017 | Write code to preview picture | 2 |  | Mikhail Burkot |  | Day 16 | 60 | 2017-10-30 | 17.6
26 | T018 | Write code to add picture and input field data to database | 2 | 1 | Mikhail Burkot | 2017-10-11 | Day 17 | 39 | 2017-10-31 | 13.2
26 | T019 | Write code to deny upload of data to website | 1 |  | Mikhail Burkot |  | Day 18 | 13 | 2017-11-01 | 8.8
26 | T020 | Write code to accept upload of data to website | 1 | 1 | Mikhail Burkot | 2017-10-11 | Day 19 | 13 | 2017-11-02 | 4.4
26 | T021 | Write code to change uploaded picture | 1 |  | Mikhail Burkot |  | Day 20 | 13 | 2017-11-03 | 0
26 | T022 | Update view locations page to display pictures from database | 3 |  | Mikhail Burkot
26 | T023 | Verify story is complete (acceptance test) | 1 |  | Mikhail Burkot
15 | T024 | Create Subscription Page | 1 | 1 | Charles Alleman | 2017-10-31
15 | T025 | Create Unsubscribe Page | 1 | 1 | Charles Alleman | 2017-10-31
15 | T026 | Create Subscription Table | 1 | 1 | Charles Alleman | 2017-10-31
15 | T027 | Create link to subscription page in modify account page | 1 | 1 | Charles Alleman | 2017-10-31
15 | T028 | Dev training in tracking changes to databases | 5 | 5 | Charles Alleman | 2017-10-31
15 | T029 | Dev training in sending mass emails | 3 | 3 | Charles Alleman | 2017-10-31
15 | T030 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31
15 | T031 | Write code to create form for subscribe page | 1 | 1 | Charles Alleman | 2017-10-31
15 | T032 | Write code to subscribe users to information about new locations | 2 | 2 | Charles Alleman | 2017-10-31
15 | T033 | Write code to send newsletter | 3 | 3 | Charles Alleman | 2017-10-31
15 | T034 | Write code to email all subscribed users | 5 | 5 | Charles Alleman | 2017-10-31
15 | T035 | Write code to identify if a location is applicable to user (based on user type) | 3 | 3 | Charles Alleman | 2017-10-31
15 | T036 | Write code to email new location to relevant subscribed users | 2 | 2 | Charles Alleman | 2017-10-31
15 | T037 | Write code to remove user from subscription | 1 | 1 | Charles Alleman | 2017-10-31
15 | T038 | Write code to add unsubscribe links to subscription emails | 2 | 2 | Charles Alleman | 2017-10-31
15 | T039 | Write code to unsubscribe user after visiting unsubscribe page | 3 | 3 | Charles Alleman | 2017-10-31
15 | T040 | Write code to inform user has been unsubscribed after visiting unsubscribe page | 1 | 0 | Charles Alleman | 2017-10-31
15 | T041 | Verify story is complete (acceptance test) | 3 | 3 | Charles Alleman | 2017-10-31
18 | T042 | Create Recommend Location Page | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T043 | Create Recommend Location Table | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T044 | Create link to recommend location page on user main page | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T045 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31
18 | T046 | Write code to create form for recommend location | 1 | 2 | Joshua Lowe | 2017-10-30
18 | T047 | Write code to add location information to database | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T048 | Write code to add location information to database when submit button pressed | 1 | 0 | Joshua Lowe | 2017-10-30
18 | T050 | Write code to inform user location information has been correctly added | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T051 | Write code to check database if location has already been added to recommended location table or location table | 2 | 0 | Joshua Lowe | 2017-10-30
18 | T052 | Write code to inform user location has already been added to system | 1 | 0 | Joshua Lowe | 2017-10-30
18 | T053 | Write code to redirect user to main page if submit or cancel button is pressed | 1 | 0 | Joshua Lowe | 2017-10-30
18 | T054 | Update user main page with link to recommend page | 1 | 1 | Joshua Lowe | 2017-10-30
18 | T055 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-10-30
24 | T056 | Create bug report page | 1 | 1 | Charles | 2017-10-14
24 | T057 | Create bug table | 1 | 1 | Charles | 2017-10-14
24 | T058 | Link bug report page to user main page | 1 | 1 | Charles | 2017-10-14
24 | T059 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31
24 | T060 | Create form for bug report | 1 | 1 | Charles | 2017-10-14
24 | T061 | Create code to add bug report form information to bug table | 1 | 1 | Charles | 2017-10-14
24 | T062 | Create code to display to user bug has been submitted | 1 | 1 | Charles | 2017-10-14
24 | T063 | Create code to redirect user to user main page | 1 | 1 | Charles | 2017-10-14
24 | T064 | Verify story is complete (acceptance test) | 1 | 1 | Charles | 2017-10-31
29 | T065 | Create user suggested locations page for admin users | 1 | 1 | Joshua Lowe | 2017-10-30
29 | T066 | Link user suggested locations to admin main page | 1 | 1 | Joshua Lowe | 2017-10-30
29 | T067 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31
29 | T068 | Write code to view suggested locations | 1 | 1 | Joshua Lowe | 2017-10-30
29 | T069 | Write code to accept suggested location | 2 | 0 | Joshua Lowe | 2017-10-30
29 | T070 | Write code to show accepted suggested location in editable form | 2 | 0 | Joshua Lowe | 2017-10-30
29 | T071 | Write code to add edited suggested location to location table and return to suggested locations page | 2 | 0 | Joshua Lowe | 2017-10-30
29 | T072 | Write code to cancel acceptance of suggested location and return to suggested locations page | 2 | 0 | Joshua Lowe | 2017-10-30
29 | T073 | Write code to deny suggested location (delete from table) | 1 | 0 | Joshua Lowe | 2017-10-30
29 | T074 | Verify story is complete (acceptance test) | 1 | 1 | Joshua Lowe | 2017-10-30
30 | T075 | Create bug report page for admin users | 1 | 1 | Charles | 2017-10-14
30 | T076 | Link bug report page to admin main page | 1 | 1 | Charles | 2017-10-14
30 | T077 | Write test cases | 1 | 1 | Mikhail Burkot | 2017-10-31
30 | T078 | Write code to view submitted bugs | 1 | 1 | Charles | 2017-10-14
30 | T079 | Write code to accept bug has been solved (delete from table) | 1 | 1 | Charles | 2017-10-14
30 | T080 | Write code to remove invalid bugs (delete from table) | 1 | 1 | Charles | 2017-10-14
30 | T081 | Verify story is complete (acceptance test) | 1 | 1 | Charles | 2017-10-14
|  |  | 114 | 85
Artefact ID | Artefact | Artefact Description | Team Member | Done?
1 | Test Cases | Write out all the test cases for sprint 1 and 2 | Mikhail | Done
2 | How-to-Guide | Step by step guide to use the website | Mikhail | Done
3
4
5
6
7 | SQL Statements | Write SQL statements | Fahd
8 | Data Model (update)
9 | Database Design (update)
10 | Populate Django Database | Populate the Django database with dummy data | Ashley | Done
11 | User Stories | New User Stories to beef up the next couple of releases | Ashley, Mikhail | Done