## Sheet1
Story ID | Priority | Points | Role | Stories - Required Features ((PRIORITY)) | Description | Team Member | Done? | INVEST-ed
1 | M | 2 | Account Holder | Account Sessions | Logging in and out of account | Ashley | Done | Done | M | 7 | 30 | 23.33%
2 | M | 1 | Visitor | Register Account | Register for an account (set location in Australia) | Misha | Done | Done | S | 8 | 30 | 26.67%
3 | M | 1 | User | Public Access Pages | Pages visible to anyone on the website | Misha | Done | Done | C | 13 | 30 | 43.33%
4 | S | 1 | Admin | Upload City Map | Upload a map of an area | Charles | Done | Done
5 | M | 2 | Account Holder | View Locations | View location information | Josh | Done | Done | 1 | 8 | 30 | 26.67%
6 | S | 1 | Account Holder | Search Locations | Search location information for all locations | Ashley | Done | Done | 2 | 8 | 30 | 26.67%
7 | S | 2 | Account Holder | Modify Account Information | Change account information (password, delete account, prefered city) | Misha | Done | Done | 3 | 7 | 30 | 23.33%
8 | S | 3 | Account Holder | View City Information | View information the city (including map) | Team | Done | Done | 4 | 2 | 30 | 6.667%
9 | M | 2 | Admin | Modify Location Data | Modify a location's details | Charles | Done | Done | 5 | 3 | 30 | 10%
10 | M | 1 | Website Owner | Website Administrator | Create Admin accounts | Team | Done | Done
Story ID | Priority | Points | Role | Stories - Possible | Description | Team Member | Done? | INVEST-ed
11 | C | 3 | Premium | Favourite Locations | Save locations to a favourites list and view them. | Fahd | Done | Done
12 | C | 3 | Premium | Website Customisation | Change the website's appearance/Personalisation options | Ashley | Done | Done
13 | C | 5 | Premium | City Location | Realtime access to a client's location | Josh | Done | Done
14 | C | 3 | Premium | Account Customisation | Allow user to customise their social profile | Team | Done | Done
15 | S | 5 | Premium | Receive email about locations/options | Receive emails about locations recently added to database before Clients | Team | Done | Done
16 | C | 4 | Client | Recommended Locations | Browse locations based on search history | Fahd | Done | Done
17 | C | 3 | Client | Recommend a Friend | Send a referral link to a friend | Misha | Done | Done
18 | C | 2 | Client | Recommend a Location | Recommend a Business/Location to an admin for them to add to the database | Fahd | Done | Done
19 | S | 3 | User | Change site language | Change the website's language | Misha | Done | Done
20 | C | 4 | User | Website accessibility options | Options for easier site navigation (invert colour, magnification,...) | Fahd | Done | Done
21 | C | 5 | User | Mobile Version | Formats the website to be workable on a mobile device | Misha | Done | Done
22 | C | 3 | Account Holder | View Location Reviews | View client-submitted reviews of locations (0-5) | Ashley | Done | Done
23 | C | 1 | Client | Submit Location Reviews | Submit a review of a location | Misha | Done | Done
24 | S | 1 | User | Website Bug Report | Submit a bug report | Misha | Done | Done
25 | C | 2 | Client | Location Sharing | Sharing a location to social media | Josh | Done | Done
26 | C | 2 | Account Holder | Upload Pictures of Locations | Upload a picture of a location | Charles | Done | Done
27 | S | 2 | Admin | Admin User Viewer | View website as a specific account user would (eg.see the site as a student) | Charles | Done | Done
28 | M | 1 | Admin | Delete Account Holder Account | Remove a User's Account | Ashley | Done | Done
29 | S | 2 | Admin | View User Suggested Locations | View all user suggested locations for the website | Charles | Done | Done
30 | C | 1 | Admin | View Website Bug Reports | View bugs found in the website